## Sheet1
COSC1076 ¦ Semester 1 2021
Assignment 2 ¦ Weekly Update Tracking Sheet
Group Name:
Group Member: | Angelo |  | Progress Classes: | Ahead
Group Member: | Henry |  |  | On-track
Group Member: | Patrick |  |  | Behind
Group Member: | Oliver |  |  | Way Behind
Tutor:
Class:
|  | Week 7 | Goals | Tutor Notes | Indidvidual Updates | Angelo | Henry | Patrick | Oliver
|  |  | Group Formed |  | Weekly Contribution | 25 | 25 | 25 | 25
|  |  | MS Team created |  | Issues | None | None | None | None
|  |  | Git Repo created |  | Other Notes | None | None | None | None
|  | Progress | On-track
|  | Week 8 | Goals | Tutor Notes | Indidvidual Updates | Angelo | Henry | Patrick | Oliver
|  |  | Choice of where to use linked list, vector & array |  | Weekly Contribution | 25 | 25 | 25 | 25
|  |  | Initial Design of ADTs (classes and potential methods) |  | Issues | Unable delete nodes | None | None | None
|  |  | Main menu |  | Other Notes | Fixed the issue | None | None | None
User Prompt (for gameplay), but no/minimal error checking
Linked List implementation
Implementation(s) or suitable ADTs wrapper for the use of vector and arrays, game logic not required
ADT implementation for storing information, game loop logic not required
|  | Progress | Behind
|  | Week 9 | Goals | Tutor Notes | Indidvidual Updates | Angelo | Henry | Patrick | Oliver
|  |  | Load/Save to/from data strucutres (doesn't require integration with main menu or game loop) |  | Weekly Contribution | 25 | 25 | 25 | 25
|  |  | Initialisation of data strctures for new game |  | Issues
|  |  | Write Tests Cases for common uses |  | Other Notes
Gameplay for single round
|  | Progress | Behind
|  | Week 10 | Goals | Tutor Notes | Indidvidual Updates | Angelo | Henry | Patrick | Oliver
|  |  | Fully complete implementation and error free |  | Weekly Contribution
|  |  | Full error checking of user prompt |  | Issues
Other Notes
Final Tests
Group Report Written
|  | Progress | Way Behind